## Sheet1
Task | Status | Priority | Sprint Points | Time Estimate | Dependencies
Executive Summary | Completed | High | 1 | 1 hour | System Diagram,
System Diagram | Completed | High | 2 | 2 hour | None
Personas and User Stories | Completed | High | 3 | 3 hour | None
Interface Diagram | Completed | High | 4 | 4 hours | Personas and User Stories
Team Roles and Qualifications | Completed | High | 0.5 | 0.5 hours | None
Development Methodology | Completed | High | 1 | 1 hour | None
Planned Scope | Completed | High | 1 | 1 hour | Product Backlog
Task Breakdown and Scheduling | Completed | High | 4 | 4 hours | Product Backlog
References | Completed | High | 0.2 | 0.2 hours | Design Doc sections
Product Backlog | Completed | High | 5 | 5 hours | Personas and User Stories, system diagram, interface diagram
Initial Product Burn-down chart | Completed | High | 0.5 | 0.5 hours | Product Backlog
Set up the starter front end code and Github repository | Completed | High | 1 | 1 hour | Finalized Design Doc
Set up the starter back end code and Github repository | Completed | High | 1 | 1 hour | Finalized Design Doc
Design the Landing Page for Self-Service Order | Completed | High | 2 | 1-2 hours | Interface Diagram
Create the menu page | Completed | Medium | 5 | 3 days | Interface Diagram
Create a Reusable Menu Item React Component | Completed | Medium | 2 | 1-2 hours | Create the menu page
Fetch Menu Item Information from the Backend | Not Started | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add a Navigation Bar for Customers | Completed | Medium | 2 | 1-2 hours | Design the Landing Page for Self-Service Order
Backend Should Process Menu Item Requests | Completed | Medium | 2 | 1-2 hours | Fetch Menu Item Information from the Backend
Create a Reusable Button Component for the Manager Interface | Completed | Medium | 2 | 1-2 hours | Create the manager landing page
Add Role-Specific Navigation Bar for Managers | Not Started | Medium | 2 | 1-2 hours | None
Create the manager landing page | Completed | Medium | 2 | 1-2 hours | Add a Navigation Bar for Customers
Reuse the Customer Menu Item Component | Completed | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create a Cashier-Specific Layout | Completed | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add Role-Specific Navigation Bar for Cashiers | Completed | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository
Implement Checkout Button (Non-Functional) | Completed | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository
Deploy the website | Completed | Medium | 1 | 1-2 hours | Set up the starter back end code and Github repository
Deploy the backend API | Completed | High | 1 | 3 hours | Set up the starter back end code and Github repository
Implement Google OAuth for Authentication (Backend) | Not Started | High | 8 | 1-3 days | Set up the starter back end code and Github repository
Add Role-Based Redirect After Login (Backend) | Not Started | High | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add Role-Based Navigation Bar Visibility (Frontend) | Not Started | High | 2 | 1-2 hours | Set up the starter back end code and Github repository, Backend Login
Implement Logout Functionality (Frontend) | Not Started | High | 2 | 1-2 hours | Set up the starter back end code and Github repository, Backend Login
Implement Login Page (Frontend) | Not Started | High | 2 | 1-2 hours | Set up the starter back end code and Github repository, Backend Login
Implement fetch request for the login (Frontend) | Not Started | High | 2 | 1-2 hours | Set up the starter back end code and Github repository, Backend Login
Add Allergen and Nutritional Information to Menu Items | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Backend Login
Display Allergen Alerts When Selecting Items | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create an API endpoint that returns the menu item components with its ingredients
Create an API endpoint that returns the menu item components with its ingredients | Not Started | High | 3 | 3 hours | Set up the starter back end code and Github repository
Implement Cart Functionality | Not Started | High | 5 | 2 days | Set up the starter back end code and Github repository
Complete ordering functionality | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create a Sales Reports Page | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create Inventory Usage Report | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository, Create Get Inventory API Endpoint
Integrate Weather API for Manager Landing Page | Not Started | High | 2 | 2 hours | Set up the starter back end code and Github repository
Create Get Inventory API Endpoint | Not Started | High | 4 | 4-5 hours | Set up the starter back end code and Github repository
Create an inventory page that displays all the information of the ingredients | Not Started | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create Get Inventory API Endpoint, Create Add Inventory API Endpoint, Create Edit Inventory API Endpoint
Create Add Inventory API Endpoint | Not Started | High | 2 | 2 hours | Set up the starter back end code and Github repository
Create Edit Inventory API Endpoint | Not Started | High | 2 | 2 hours | Set up the starter back end code and Github repository
Create Frontend Form for Adding/Editing ingredients | Not Started | Medium | 2 | 1-2 hours | Set up the starter back end code and Github repository
Validation and error handling for Add/Edit Inventory | Not Started | High | 8 | 1-3 days | Set up the starter back end code and Github repository
Create Delete Inventory API Endpoint | Not Started | High | 3 | 3 hours | Set up the starter back end code and Github repository
Create Frontend Button for Deleting Ingredients | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create Delete Inventory API Endpoint
Error Handling for Ingredient Delete Operation | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create Admin Page Layout | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Add Buttons to Trigger Add or Edit Mode
Add Navigation Link to Admin Page in Manager Landing Page | Not Started | High | 1 | 1 hours | Set up the starter back end code and Github repository
Create Add Employee API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create Edit Employee API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Add Buttons to Trigger Add or Edit Mode | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create Add Employee API Endpoint, Create Edit Employee API Endpoint
Design Unified Edit/Add Employee Form | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Handle Validation and Error Messaging in the Unified Form | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create a landing page for the menu page | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Design the Menu Items Page Layout | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create Add Menu Item API Endpoint, Create Edit Menu Item API Endpoint
Create Add Menu Item API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create Edit Menu Item API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create Delete Menu Item API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Implement Menu Item Add/Edit Form with Conditional Logic | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add Buttons to Navigate to Menu Item Components | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Design the Menu Item Components Page Layout | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create Add Item Component API Endpoint, Create Edit Item Component API Endpoint
Create Add Item Component API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create Edit Item Component API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create Delete Item Component API Endpoint | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Implement Item Component Add/Edit Form with Conditional Logic | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Create Add Item Component API Endpoint, Create Edit Item Component API Endpoint
Manage Ingredients within Components | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create a Reviews Section in the Menu Item Component | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Set Up Backend API to Retrieve Reviews | Not Started | High | 5 | 5-4 hours | Set up the starter back end code and Github repository
Create Reviews database table | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Display Average Rating and Number of Reviews | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add a 'Leave a Review' Button to the Menu Item Component | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Build a Review Submission Form | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Implement Backend API for Review Submission
Implement Backend API for Review Submission | Not Started | High | 3 | 1-3 hours | Set up the starter back end code and Github repository
Validate and Display Customer Reviews in Real Time | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create a Review Summary Report for Managers | Not Started | High | 5 | 5 hours | Set up the starter back end code and Github repository
Display the Review summary report under Reports Page | Not Started | High | 4 | 4 hours | Set up the starter back end code and Github repository
Implement Frontend Form Validation | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Set Up Backend Error Handling | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Integrate Frontend Error Boundaries | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Automated Testing Suite | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create Order History Page | Not Started | High | 8 | 1 day | Set up the starter back end code and Github repository
Develop Backend API to Fetch Order History | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Design Order Summary Cards or Table | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Implement Search and Filter Functionality | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Error Handling and Loading States | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Integrate Google Translate API into the kiosk interface | Not Started | High | 4 | 3-4 hours | Set up the starter back end code and Github repository
Create a dropdown menu on the main screen for language selection | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Ensure all menu text, buttons, and labels dynamically update when a language is selected | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Design icons and buttons with a larger-than-standard size | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Use universally recognized symbols for actions | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Develop a toggle switch on the main screen to enable high-contrast mode | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Create a separate high-contrast color scheme | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Ensure that all images, text, and icons adjust to the high-contrast setting | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add a text resizing feature on the main screen | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Ensure that resized text adapts fluidly across all layouts | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Test functionality with screen magnifiers | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository, Add a text resizing feature on the main screen
Provide a 'Text Size' button directly on each page | Not Started | Medium | 5 | 4-6 hours | Set up the starter back end code and Github repository
Implement large, readable text settings | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add descriptive alt text to each image and icon | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Verify screen reader compatibility | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Integrate a text-to-speech (TTS) option | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Add a 'Read Aloud' button next to each main section | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Ensure universal icons and symbols are easily understood | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Design a streamlined layout with minimal elements per page | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Group related items for clarity | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Design Display-Only Interface Layout for Multi-Display | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Develop a Responsive Layout to Adapt to Large Screens | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Implement Auto-Scroll or Slide Features | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Configure Backend for Real-Time Updates | Not Started | Low | 2 | 1-2 hours | Set up the starter back end code and Github repository
Ensure Consistency of Displayed Menu and Promotional Information | Not Started | Low | 2 | 1-2 hours | Website completed
291.2